## 100 Day SEO Plan
S.NO | Timeline | SEO Plan | Days
1 | Phase 1: Foundation | Audit + Strategy Setup | Day 1–20
2 | Day 1–3 | Full website audit (SEO + UX + mobile) | 3
3 | Day 4–5 | Competitor analysis | 2
4 | Day 6–8 | Keyword research | 3
5 | Day 9–11 | Messaging revamp | 3
6 | Day 12–14 | Fix technical SEO | 3
7 | Day 15–17 | Mobile UX restructuring | 3
8 | Day 18–20 | Setup tools | 3
9 | Phase 2: Conversion | Website + Funnel Build | Day 21–50
10 | Day 21–25 | Rewrite homepage | 5
11 | Day 26–30 | Create landing pages | 5
12 | Day 31–34 | Create feature pages | 4
13 | Day 35–38 | Add lead magnets | 4
14 | Day 39–42 | Add CTAs & popups | 4
15 | Day 43–46 | Build demo funnel | 4
16 | Day 47–50 | Add trust elements | 4
17 | Phase 3: Content | Traffic + Authority | Day 51–75
18 | Day 51–55 | Create pillar pages | 5
19 | Day 56–60 | Write blogs | 5
20 | Day 61–63 | BOFU blogs | 3
21 | Day 64–66 | Optimize content | 3
22 | Day 67–70 | Publish case studies | 4
23 | Day 71–75 | Add FAQs + schema | 5
24 | Phase 4: Growth | Scale + Optimize | Day 76–100
25 | Day 76–80 | Build backlinks | 5
26 | Day 81–85 | Social funnel | 5
27 | Day 86–88 | A/B testing | 3
28 | Day 89–92 | Improve UX | 4
29 | Day 93–96 | Retargeting ads | 4
30 | Day 97–100 | Scale + roadmap | 4